## Tracker
Sr. No. | Category | Particulars | Internal / External | Phase I / Phase II | ICICI / I Spirit | Present Status | ICICI Bank FPR | Timelines
1 | Policy framework | Policy framework for Invoice discounting | Internal | Phase 1 | ICICI Bank | Pilot approval to be taken
2 |  | > Considering history of invoices | Internal | Phase 1 | ICICI Bank
3 |  | > GST & Bank statement | Internal | Phase 1 | ICICI Bank
4 | Origination for Invoice Discounting | Platform/ Database to handle BHIM requests (Invoice Discounting product) | Internal | Phase 1 | ICICI Bank | Done through API
5 |  | Limit storage in LOP / Database | Internal | Phase 1 | ICICI Bank | Storage in data base being worked out
6 |  | Storage of customer information for cross sell opportunity | Internal | Phase 1 | ICICI Bank
7 | Onboarding | Derived KYC for individuals / Non Individuals | External | Phase 1 | I Spirit
8 |  | Policy framework for KYC, High risk KYC | External | Phase 1 | I Spirit
9 | BRE Development | Modification in existing BREs for incorporation of invoices & buyer seller relationships | Internal | Phase 1 | ICICI Bank | One round of discussion done for modification
10 |  | Including BRE for pricing decision basis buyer seller relationship | Internal | Phase 1 | ICICI Bank | Rule to be framed
11 | Underwriting | AA details for underwriting Duration for which bank statement will be shared at time of under-writing. Identification of Savings , Current or OD account statement | External | Phase 1 | I Spirit
12 |  | PCR Lite integration | External | Phase 1 | I Spirit
13 |  | Bureau – Impact of multiple banks hitting bureau for same customer | External | Phase 1 | I Spirit
14 |  | API Intergration for AA , GST , Bureau , CPCS | Internal | Phase 1 | ICICI Bank | Done
15 |  | Platform Integrations required - AA , GST , Bureau , CPSCS , PCR | Internal | Phase 2 | ICICI Bank | To be intiated
16 | Loan Disbursement | Loan booking system to be used for disbursement | Internal | Phase 1 | ICICI Bank | Discussion done with Core team on 27th . Reverts expected by 28th EOD
17 |  | 2. OTP Integration | External | Phase 1 | I Spirit
18 |  | 3. Loan agreement closure | Internal | Phase 1 | ICICI Bank
19 |  | Overall limit setup & Sublimit Set up in finacle | Internal | Phase 1 | ICICI Bank | To be intiated
20 |  | e-Mandate setup | Internal | Phase 1 | ICICI Bank | To be intiated
21 |  | Discovery of CA accounts for eMandate setup | Internal | Phase 1 | ICICI Bank | To be intiated
22 |  | PCR reporting post disbursement | External | Phase 1 | I Spirit
23 |  | Service response packet for BHIM | External | Phase 1 | I Spirit
24 |  | PSL categorisation norms | External | Phase 1 | I Spirit
25 | Monitoring | Structure of e-mandate for invocation | External | Phase 1 | I Spirit
26 |  | e-Mandate setup for repayment of loans. Repayment to loan specific offers. | Internal | Phase 1 | ICICI Bank | To be intiated
27 |  | Monitoring rules and triggers for each loans details received from AA's in ICICI Platform / Database | Internal | Phase 1 | ICICI Bank | To be intiated
28 |  | EWS configuration in ICICI Platform / Database | Internal | Phase 1 | ICICI Bank | To be intiated
29 | Logs | Storage of log of AA and offer for audit , further analysis & generation | External | Phase 1 | I Spirit
30 |  | Bureau – Impact of multiple banks hitting bureau for same customer | External | Phase 1 | I Spirit
31 | Cross Sell Limit availment | Online PA offer generation | Internal | Phase 2 | ICICI Bank | To be intiated
32 |  | Offer communication to customers | Internal | Phase 2 | ICICI Bank | To be intiated
33 |  | KYC validations - thru CKYC / Video KYC | Internal | Phase 2 | ICICI Bank | To be intiated
34 |  | API account opening | Internal | Phase 2 | ICICI Bank | To be intiated
35 |  | Cross sell limit setup | Internal | Phase 2 | ICICI Bank | To be intiated